## Gantt Chart
Task Name | Start Date | End Date | Status | Duration | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22
Design Phase | 2025-01-02 | 2025-01-06 | Completed | 5
Development | 2025-01-06 | 2025-01-10 | In Progress | 5
Testing | 2025-01-08 | 2025-01-12 | Not Started | 5
Deployment | 2025-01-13 | 2025-01-18 | Not Started | 6
Review | 2025-01-19 | 2025-01-20 | Not Started | 2
Design Notes:
First off, this worksheet has frozen panes for ease of scrolling and navigation!
Column D (Status) - has conditional formatting automatically making the cells change color - Completed = green, In Progress = Yellow, Not Started = blue.
Column E (Duration) - is calculated as a difference between end date and start date to calculate duration of the task. Remember. in Excel, duration calculation will be End Date minus Start date, but will be one day short, so that is why the formula must contain +1, so the duration includes the start day itself as well...
Columns F-Z (Dates) - contains conditional formatting rules. We need to have two rules per cell - one will make cells grey for completed items and one make them teal color for unfinished ones. There is one very important thing you need to keep in mind: the below formulas will be doinbg a mathematical operation, so all your date cells have to be formatted as dates: if your formulas are not working, be sure you check your formatting! If something looks like a date it doesn't automatically mean it is a date! Excel may be seeing it as an ordinary text string. First rule calculates as follows: IF F1>=B2 AND F1 <= C2 AND D2 = Completed, then the rule will turn the cell grey. All three of these conditions must be met for the rule to be true. What this formula does is: if the Date in column F is after or on the Start Date AND if the Date in F is before or on End Date AND the Status column value is Completed, then the formula result is true = all three conditions are met = cell will be turned grey.
Second rule is nearly identical to the first, except we remove the third condition about completeness, so this rule only looks whether the particular date in columns F-Z falls on or between the start and end date as follows: IF F1>=B2 AND F1 <= C2 then the two rule conditions are met and the rule will turn the cell teal color. Again, what this rule does is to take date from column F for example, compares it to the start date to see whether it is bigger or equal, then compares it to the end date and sees whether it is smaller or equal to end date. If both conditions return positive (true), then the rule is met and turns the cell teal colored.
Making it yours:
When expanding this there is one very important thing to keep in mind. If you look at the formulas in Home >> Conditional Formatting >> Manage Rules you will notice that the formulas contain ABSOLUTE REFERENCES with $ signs in front of columns! It is CRITICAL you have the $ signs there, because if you want to copy this formatting to other cells as you expand this table with more dates and rows, the $ ensure that the formula keeps locked onto the reference columns (start date, end date, status). Because if you don't and try to paste this formatting to cells to the right, it will move the formula equal amount of columns and no longer read your dates and give you completely wrong results!!! I've written an article about how absolute references work. See my website.
=AND(F$1>=$B2, F$1<=$C2, $D2="Completed")
=AND(F$1>=$B2, F$1<=$C2)
Read my blog article on https://goarcherdynamics.com on how to make this Gantt Chart (just search my site) where I descirbe precise step-by-step instructions on how to set this spreadsheet up from scratch.
contact@goarcherdynamics.com